Assignment No. 03

Due Date:

Your assignment must be uploaded/submitted before or on 13th June 2011

Uploading instructions:

Please view the Assignment Submission Process document provided to you by the Virtual University for uploading assignments.

- Assignment should be in .doc format.

- Save your assignment with your ID (e.g. bx020200786.doc).

- Assignment submission through email is highly discouraged.

Rules for Marking:

It should be clear that your assignment will not get any credit if:

- The assignment is submitted after due date.

- The submitted assignment file is corrupted.

- The assignment is copied.

Note:

Your answer must follow the below given specifications. You will be assigned zero marks if you do not follow these instructions.

- Font style: “Times New Roman”

- Font color: “Black”

- Font size: “12”

- Bold for heading only.

- Font in Italic is not allowed at all.

- No formatting or bullets are allowed to use.

Total Marks = 20

Q.

Let us assume that you are working as a project manager in a multinational company. You were asked to compute the earned value analysis of a software project. The software project has 80 planned work tasks that are estimated to require 690 person-days to complete. At the time you have been asked to do the earned value analysis, 12 tasks have been completed. However, the project schedule indicates that 17 tasks should have been completed. The following scheduling data in person-days are available:

| Task | Planned Effort | Actual Effort |
| --- | --- | --- |
| 1 | 14 | 12.5 |
| 2 | 12 | 13 |
| 3 | 11 | 11 |
| 4 | 10 | 9.5 |
| 5 | 9 | 9 |
| 6 | 8 | 9 |
| 7 | 12 | 12 |
| 8 | 4 | 5 |
| 9 | 7 | 7.5 |
| 10 | 13 | 12.5 |
| 11 | 6 | 6 |
| 12 | 8 | 8 |
| 13 | 9 |  |
| 14 | 15 |  |
| 15 | 11 |  |
| 16 | 5 |  |
| 17 | 6 |  |

Compute the following

- SPI

- Schedule variance

- Percent scheduled for completion

- Percent complete

- CPI

- Cost variance for the project.